## Tracker
Track Installation
Segment | Planned Mi | Completed Mi (Previous) | Completed Mi (Current) | % Completion | Completed Mi % (Previous) | Completed Mi % (This Week) | Notes
Central Urban Corridor | 19 mi | 12 mi | 16 mi | 84% | 63.16% | 21.05% | Advanced machinery and night shifts increased pace. Monitor potential community noise concerns.
Southeastern Quadrant | 15 mi | 6 mi | 4 mi | 67% | 40% | 27% | Recent equipment upgrades significantly improved installation rate. Continued focus on maintaining momentum.
Eastern Section | 12 mi | 6 mi | 6 mi | 50% | 50% | 0% | No progress due to rocky terrain. Exploring alternative methods and potential rerouting. Strategic review needed.
Western Industrial Area | 22 mi | 9 mi | 16 mi | 73% | 40.91% | 31.82% | Accelerated progress with enhanced equipment deployment. Optimize resource allocation to sustain pace.
Electrification
Component | Planned Units | Completed Units (Previous) | Completed Units (Current) | % Completion | Completed Units % (Previous) | Completed Units % (This Week) | Notes
Track Electrification | 68 mi | 24 mi | 6 mi | 44% | 35.29% | 9% | Significant progress with 6 mi electrified recently. Continuing efforts to stay on track.
Substations Construction | 5 mi | 2 mi | 2 mi | 40% | 40% | 0% | No new substations completed. Delay in electrical components impacts schedule.
Section | Planned Miles | Completed Miles
Eastern | 12 | 6
Southeastern | 15 | 10
Electrification Progress
Planned Miles | 68
Completed Miles | 30
Budget Overview
Budgeted (M) | 125
Spent (M) | 90

## Dashboard
Metroville Rail Expansion Project Dashboard
[10 empty] | Status Update |  | Challenges
Main Numbers / KPIs |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Total Track Planned (Miles) | 27 | Phase 1 | [7 empty] | ✅ 30 miles electrified successfully |  | · Delay due to rocky terrain - 6mi behind schedule
Total Track Completed (Miles) | 16 | Phase 2 | [7 empty] | ✅ 10 miles track completed in Southeastern Quadrant |  | ACTION: in progress evaluation of alternative method to expedite progress
Electrification Planned (Miles) | 68 | Phase 3 | [7 empty] | ✅ Community engagement efforts well appreciated |  | · Overspent in the excavation
Electrification Completed (Miles) | 30 | Phase 4 | [9 empty] | ACTION: Savings on materials have offset this, keeping us
Budget (M) | 125 | [10 empty] | within 5% of our overall budget projection for this phase.
Spent (M) | 90
Progress- Completion% | [8 empty] | Project Financials |  | Community Feedback Highlights
Strong appreciation for community engagement and transparency.
Significant complaints about nighttime construction noise in the Eastern Section.
Relevant Risks
⚠️ Delays in Eastern Section due to rocky terrain
⚠️ Nighttime construction noise complaints
⚠️ Budget tracking slightly over projected costs